# 21 December 2007

[9-07]

PROPOSAL – ADMINISTRATIVE ASSESSMENT

| P1001 | Date Administrative Assessment Completed (proposal prepared): 17 December 2007 |  |  |
| --- | --- | --- | --- |
| Title: Omnibus VII Brief Description of Proposal: To amend the Code to correct minor errors, inconsistencies and ambiguities and to amend food regulatory measures in the Code as a result of an audit of editorial notes. |  |  | Potentially Affected Standards in the Code: Various Standards throughout the Code |
| Procedure: General Reasons why: Minor amendments requiring only a single round of consultation |  | Cost Category (General Procedure): (Level 1) Up to 500 hours Reasons why: Numerous minor amendments with limited social or economic impact, no need for an assessment of the risk to public health and safety, simple assessment of risk management requirements. | Estimated start work: 4th Qtr 2007 |

Other Comments or Relevant Matters:

## DECISION

Proposal prepared Date: 17 December 2007

CONSULTATION & ASSESSMENT TIMEFRAME

| ## Consultation Strategy: Proposed length of public consultation period: General Procedure (6 weeks) | Community Involvement Category: 5 (minor significance or complexity) |
| --- | --- |
| Proposed Timeframe for Assessment: ‘Early Bird Notification’ due: General Procedure: Commence Assessment (clock start) Mid-December 2007 Completion of Assessment Mid-January 2008 Public comment Late January – early March 2008 Board to complete Approval Mid-April 2008 (OOS) Notification to Ministerial Council Late April 2008 Anticipated gazettal if no review requested Early July 2008 |  |