20 March 2009

[4-09]

PROPOSAL – ADMINISTRATIVE ASSESSMENT

| P1005 | Date Administrative Assessment Completed (proposal prepared): 10 March 2009 |  |  |
| --- | --- | --- | --- |
| Title: Primary Production & Processing Standard for Meat & Meat Products Brief Description of Proposal: To examine the meat supply chain in Australia and develop a national food safety standard covering meat and meat products from farmed cattle, pigs, sheep and goats, harvested goats and rendered products. Farmed minor meat species, emu/ostrich meat and wild game animals will be addressed later. |  |  | Potentially Affected Standards in the Code: 1.6.1 Microbiological Limits for Food (Australia only) 1.6.2 Processing requirements (Australia only) 2.2.1 Meat and Meat Products 4.2.3 Primary Production and Processing Standard for Meat (Australia only) |
| Procedure: Major Reasons why: - Involves the development of, or variation to new food regulatory measures. - Requires consideration of the entire meat supply chain (i.e. from paddock-to-plate for all meat animal species). - Requires extensive consultation with all stakeholders and involves the creation and engagement of expert advisory groups. - Will require a minimum of two rounds of public consultation. |  | Cost Category (General Procedure): Estimated total hours (Major Procedure) 7070 | Estimated start work: 1st Qtr 2009 |

## DECISION

Proposal prepared Date: 10 March 2009

CONSULTATION & ASSESSMENT TIMEFRAME

| ## Consultation Strategy: Proposed length of public consultation periods: Major Procedure post-1st Assessment (8 weeks) Post-2nd Assessment (8 weeks) Specific consultation methods also include: - The Standard Development Committee and any sub-group of that - Participation at industry meetings | Community Involvement Category: 3 Intensive narrower focus |
| --- | --- |
| Proposed Timeframe for Assessment: Major Procedure: Commence Assessment (clock start) mid-March 2009 Completion of 1st Assessment mid-Sept 2009 Public comment late Sept 2009 – early Nov 2009 Completion of 2nd Assessment mid-May 2010 Public comment mid-May 2010 – late June 2010 Board to complete Approval mid-Sept 2010 Notification to Ministerial Council late Sept 2010 Anticipated gazettal if no review requested mid-Dec 2010 |  |