

**27 June 2019**

**[85–19]**

**Administrative assessment report – Proposal P1010**

Review of Formulated Supplementary Sports Foods

|  |  |  |
| --- | --- | --- |
| **Brief Description of Proposal :**  To review Standard 2.9.4 – Formulated Supplementary Sports Foods (FSSF) of the *Australia New Zealand Food Standards Code* | | **Potentially affected standard:**  2.9.4 – FSSF  1.2.7 – Nutrition, Health and Related Claims |
| **Procedure:**  Major  **Reasons why:**  The proposal will review an entire standard that is 20 years old and out of date. | **Estimated total hours:**  Two stages are planned for this proposal  Stage 1 ~2300 hours  Stage 2 TBD  **Reasons why:**  Stage 1 will inform the project scope and issues for the proposal. It will comprise a situational analysis including the trade, sale, education and use of FSSF by various sectors including industry, the sports and broader community and government.  Stage 1 will also examine the operation of ANZ food/supplemented food/therapeutic good regulatory context for sports products including the food medicine interface.  Stage 2 will involve development of revised arrangements for regulation of sports food. | **Provisional estimated start work:**  Late June 2019 |

|  |
| --- |
| **Other Comments or Relevant Matters:**  In October 2018, the Forum requested FSANZ to conduct a full review of Standard 2.9.4 – Formulated Supplementary Sports Food as a matter of priority to modernise the Standard. |

***Decision***

|  |
| --- |
| **Proposal prepared**  Date: 14 June 2019 |

***Consultation & assessment timeframe***

|  |  |
| --- | --- |
| **Proposed length of public consultation periods**  At least two opportunities for public consultation are planned during the assessment of the Proposal. Additional rounds of public comment are expected given the large number of issues to be assessed. Depending on the range of issues, longer consultation periods will be considered.  Formal consultation will be complemented by extensive targeted consultation with key stakeholders. | |
| **Proposed timeframe for assessment:**  **Stage1:**  Commence assessment (clock start)  Targeted consultation  Preparation of first consultation paper  Public comment  Preparation of second consultation report, if required  Situational analysis report  **Stage 2**  Completion of assessment  Public comment  Preparation of draft food regulatory measure  Public comment  Additional consultation paper, if required  Board to complete approval  Notification to Forum  Anticipated gazettal if no review requested | June 2019  June 2020  TBD |