2 November 2011

[21-11]

PROPOSAL – ADMINISTRATIVE ASSESSMENT

| P1014 | Date Administrative Assessment Completed (proposal prepared): 20 October 2011 |  |  |
| --- | --- | --- | --- |
| Title: Primary Production & Processing Standard for Minor Meat Species & Wild Game Brief Description of Proposal: - To develop an Australia only primary production and processing standard for meat and meat products from minor species and wild game to provide a nationally consistent approach to the management of meat safety. The development of a standard for the farmed major species (cattle, sheep, pigs and goats) is being undertaken under Proposal P1005. |  |  | Potentially Affected Standard/s in the Code: 1.6.2 – Processing requirements 2.2.1 – Meat and Meat Products 4.2.3 – Primary Production & Processing Standard for Meat |
| Procedure: Major The proposal involves such scientific or technical complexity that it is necessary to adopt this procedure in considering it |  | Estimated total hours: 2335 Requires consideration of the entire meat supply chain (i.e. from paddock-to-plate for all minor species and wild game species). Requires extensive consultation with stakeholders and involves the creation and engagement of advisory groups. Will require a minimum of two rounds of public consultation. | Estimated start work: October 2011 |

Other Comments or Relevant Matters:

## DECISION

Proposal prepared Date: 20 October 2011

CONSULTATION & ASSESSMENT TIMEFRAME

| ## Consultation Strategy: Proposed length of public consultation periods: Major Procedure post-1st Assessment (8 weeks) Post-2nd Assessment (8 weeks) Specific consultation methods also include: - The Meat and Meat Products Standard Development Committee and a specific Working Group reflecting the minor species and wild game sectors - Industry visits | Community Involvement Category: 3 Intensive narrower focus |
| --- | --- |
| Proposed Timeframe for Assessment: Major Procedure: Commence Assessment (clock start) Late October 2011 Completion of 1st Assessment Early March 2012 Public comment Mid-March 2012 – Mid May2012 Completion of 2nd Assessment Mid-September 2012 Public comment Late September– Late November 2012 Board to complete Approval Mid-April 2013 Notification to Ministerial Council Late April 2013 Anticipated gazettal if no review requested Early July 2013 |  |