16 February 2012

[3-12]

PROPOSAL – ADMINISTRATIVE ASSESSMENT

| P1016 | Date Administrative Assessment Completed (proposal prepared): 2 February 2012 |  |  |
| --- | --- | --- | --- |
| Title: Hydrocyanic Acid in Apricot Kernels & Other Foods Brief Description of Proposal: To consider an amendment to the Code for hydrocyanic acid in raw apricot kernels, foods derived from them and potentially other foods. |  |  | Potentially affected Standards in the Code: 1.2.3 1.2.6 1.4.1 1.4.4 |
| Procedure: General Amendment (s) to the Code requiring only a single round of consultation. |  | Estimated total hours: Maximum of 1000 hours Reasons why: FSANZ will conduct a risk assessment of greater than average complexity. Food regulatory options, commensurate with risk assessment findings and legal drafting, will also be considered. | Estimated start work: December 2011 |

Other Comments or Relevant Matters:

## DECISION (SMO to complete AFTER Delegate makes a decision)

Proposal prepared Date: 2 February 2012

CONSULTATION & ASSESSMENT TIMEFRAME

## Consultation Strategy: Proposed length of public consultation period: 6 weeks

Proposed Timeframe for Assessment: Commence assessment (clock start) Early March 2012 Completion of assessment & preparation of draft food reg measure Late July 2012 Public comment Early August-late Sept 2012 Board to complete consideration Early December 2012 Notification to FoFR Mid-December 2012 Anticipated gazettal if no review requested Late February 2013