16 February 2012

[3-12]

PROPOSAL – ADMINISTRATIVE ASSESSMENT

| P1017 | Date Administrative Assessment Completed (proposal prepared): 6 February 2012 |  |  |
| --- | --- | --- | --- |
| Title: Criteria for Listeria monocytogenes – Microbiological Limits for Foods Brief Description of Proposal: To update Standard 1.6.1 with regards to criteria for Listeria monocytogenes limits in ready-to-eat foods; aligning with international (Codex) standards, Food Safety and Primary Production and Processing Standards and associated FSANZ guidance material. |  |  | Potentially Affected Standard in the Code: Standard 1.6.1 – Microbiological Limits for Food |
| Procedure: Major Reasons why: This proposal involves scientific and technical complexity and proposes changes to current food regulatory measures. |  | Estimated total hours: 1200 hours Reasons why: Requires extensive consultation with stakeholders and the creation and engagement of a technical working group. | Estimated start work: February 2012 |

Other Comments or Relevant Matters:

## DECISION

Proposal prepared Date: 6 February 2012

CONSULTATION & ASSESSMENT TIMEFRAME

## Consultation Strategy: Proposed length of public consultation period: 1st call for submissions (8 weeks) 2nd call for submissions (8 weeks) Specific consultation methods also include: - The engagement of a technical working group

Proposed Timeframe for Assessment: Commence assessment (clock start) Mid-February 2012 Completion of assessment Early May 2012 Public comment Mid-May 2012 – Mid-July 2012 Preparation of draft food reg measure Early December 2012 Public comment Mid December – Late February 2013 Board to complete Approval Late July 2013 Notification to Forum Late July 2013 Anticipated gazettal if no review requested Early October 2013