16 February 2012

[3-12]

PROPOSAL – ADMINISTRATIVE ASSESSMENT

| P1018 | Date Administrative Assessment Completed (proposal prepared): 6 February 2012 |  |  |
| --- | --- | --- | --- |
| Title: Companion Dogs in Outdoor Dining Areas Brief Description of Proposal: To remove restrictions on the presence of companion dogs in outdoor dining areas of food premises. |  |  | Potentially affected Standard in the Code: 3.2.2 |
| Procedure: General |  | Estimated total hours: Max 350 hours Reasons why: A risk assessment has been completed; some liaison with jurisdictions has already occurred and potential changes to Standard 3.2.2 to reflect more suitable and consistent regulatory measures are considered minor. | Estimated start work: February 2012 |

Other Comments or Relevant Matters:

## DECISION

Proposal prepared Date: 6 February 2012

CONSULTATION & ASSESSMENT TIMEFRAME

## Consultation Strategy: Proposed length of public consultation period: 6 weeks

Proposed Timeframe for Assessment: General Procedure: Commence Assessment (clock start) Late February 2012 Completion of assessment & preparation of draft food reg measure Early April 2012 Public comment Mid-April–late May 2012 Board to complete Approval Late July 2012 Notification to Forum Early August 2012 Anticipated gazettal if no review requested Mid-October 2012