17 December 2012

[29-12]

Administrative Assessment Report – Proposal P1024

Revision of the Regulation of Nutritive Substances & Novel Foods

| Brief Description of Proposal: To develop an alternative framework for the regulation of nutritive substances (currently defined in Standard 1.1.1) and novel foods (currently regulated in Standard 1.5.1) in the Code |  | Potentially affected Standards: 1.1.1, 1.3.2, 1.5.1, 2.6.4, Part 2.9 standards that refer to nutritive substances |
| --- | --- | --- |
| Procedure: Major Reasons why: Involves review and resolution of complex regulatory issues and engagement of multiple stakeholders. | Estimated total hours: 2310 Reasons why: Multi-disciplinary project within FSANZ requiring responses to two calls for submissions. The need for targeted consultation is also anticipated. | Estimated start work: November 2012 |

Decision

Proposal prepared Date: 13 December 2012

Consultation & assessment timeframe

Proposed length of public consultation periods: 1st call for submissions (8 or 10 weeks) (depends on when decision made) 2nd call for submissions (8 weeks)

Proposed timeframe for assessment: Commence assessment (clock start) Mid-Dec 2012 Completion of assessment Late April 2013 Public comment Early May–early July 2013 Preparation of revised draft food regulatory measure Mid-Oct 2013 Public comment Late Oct–late Dec 2013 Board to complete approval Early May 2014 Notification to Forum Early May 2014 Anticipated gazettal if no review requested Mid-July 2014