19 March 2013

[04-13]

Administrative Assessment Report – Proposal P1026

Lupin as an Allergen

| Brief Description of Proposal: To consider options to regulate food containing lupin as a food allergen. |  | Potentially affected Standard: 1.2.3 |
| --- | --- | --- |
| Procedure: General | Estimated total hours: Up to 650 Reasons why: Investigate new labelling requirements for food containing lupin. | Estimated start work: March 2013 |

Decision

Proposal prepared Date: 1 March 2013

Consultation & assessment timeframe

Proposed length of public consultation period: 6 weeks

Proposed timeframe for assessment: Commence assessment (clock start) Early March 2013 Completion of assessment & preparation of draft food reg measure Early June 2013 Public comment Mid-June – late July 2013 Board to complete approval Early Dec 2013 Notification to Forum Mid-Dec 2013 Anticipated gazettal if no review requested Late Feb 2014