

**2 May 2014**

**[07-14]**

**Administrative Assessment Report – Proposal P1032**

Code Maintenance XI

|  |  |  |
| --- | --- | --- |
| **Brief Description of Proposal:**  to make minor amendments including the correction of typographical errors, inconsistencies and formatting issues and updating of references. | | **Potentially affected Standards:**  Various standards |
| **Procedure:**  Minor  Reasons why:  Section 66 of the FSANZ Act applies as FSANZ is only proposing variations to the Code that *do not*:  (a)impose, vary or remove an obligation on any person; or  (b)create, vary or remove a right of any person; or  (c)otherwise alter the legal effect of a food regulatory measure. | **Estimated total hours:**  Max 100 hours | **Estimated start work:**  April 2014 |

|  |
| --- |
| **Other Comments or Relevant Matters:**  Pursuant to section 68 of the FSANZ the Act, FSANZ will consult with appropriate government agencies as well as affected stakeholders on the proposed amendments. Other members of the public are welcome to provide comments at this time. |

***Decision***

|  |
| --- |
| **Proposal prepared**  Date: 28 April 2014 |

***Consultation & assessment timeframe***

|  |
| --- |
| **Proposed length of public consultation period:**  4 weeks |
| **Proposed timeframe for assessment:**  Commence assessment (clock start) Mid-May 2014  Completion of assessment & preparation of draft food reg measure Mid-June 2014  Public comment Mid-June–mid-July 2014  Board to complete approval Mid-Aug 2014  Notification to Forum Late Aug 2014  Anticipated gazettal if no review requested Early Nov 2014 |